SQUAD
PROD

VIDEO PRODUCTION BRIEF

Editable planning template for brands and organisations in Morocco

Use this document before asking for a fixed quotation. Complete what is known, mark assumptions, and assign one final approver. A strong brief makes concepts, schedules, rights and deliverables more reliable.

VERSION 1.0  /  AUGUST 2026

# How to use this brief

Three rules 1. Describe the business decision before the visual style. 2. Separate confirmed facts from assumptions. 3. One person consolidates feedback and gives final approval.

## 24-point readiness score

Score each decision: 0 = unknown, 1 = partly defined, 2 = confirmed. Below 16/24, request discovery rather than a fixed quote. 16–19 supports a provisional estimate. 20–24 usually supports a treatment and reliable schedule. This is a SQUADPROD planning tool, not an industry standard.

| Decision | Score | What is confirmed / missing |
| --- | --- | --- |
| Objective | 0 / 1 / 2 | Notes: __________________________________ |
| Audience | 0 / 1 / 2 | Notes: __________________________________ |
| Single message | 0 / 1 / 2 | Notes: __________________________________ |
| Desired action | 0 / 1 / 2 | Notes: __________________________________ |
| Platforms | 0 / 1 / 2 | Notes: __________________________________ |
| Deliverables | 0 / 1 / 2 | Notes: __________________________________ |
| Languages | 0 / 1 / 2 | Notes: __________________________________ |
| Proof | 0 / 1 / 2 | Notes: __________________________________ |
| Creative boundaries | 0 / 1 / 2 | Notes: __________________________________ |
| Usage rights | 0 / 1 / 2 | Notes: __________________________________ |
| Timing | 0 / 1 / 2 | Notes: __________________________________ |
| Final approver | 0 / 1 / 2 | Notes: __________________________________ |

| TOTAL / 24 | ________ / 24 |
| --- | --- |

# 01  Project and ownership

| Project / campaign name | ________________________________________________________________ |
| --- | --- |

| Company / brand | ________________________________________________________________ |
| --- | --- |

| Project owner | Name, role, email, phone |
| --- | --- |

| Final approver | One person only |
| --- | --- |

| Contributors | Marketing, sales, legal, operations, agency |
| --- | --- |

| Production contact | ________________________________________________________________ |
| --- | --- |

| Target launch date | ________________________________________________________________ |
| --- | --- |

| Budget band | Dhs __________________ |
| --- | --- |

## Objective and decision

| After watching, the audience should... | ________________________________________________________________ ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| Business outcome / KPI | Qualified leads, bookings, applications, awareness, sales support... ________________________________________________________________ |
| --- | --- |

| Current problem | ________________________________________________________________ ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

# 02  Audience, message and proof

| Primary audience | Role, situation, geography, language, awareness ________________________________________________________________ |
| --- | --- |

| What they want | ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| Main objection / fear | ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| Single message | If the viewer remembers one idea... ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| Desired action | Book, contact, visit, apply, understand, trust... ________________________________________________________________ |
| --- | --- |

## Proof inventory

| Proof / claim | Evidence available | Owner | Approved? |
| --- | --- | --- | --- |
| 1 |  |  | [ ] |
| 2 |  |  | [ ] |
| 3 |  |  | [ ] |
| 4 |  |  | [ ] |
| 5 |  |  | [ ] |

# 03  Channels and deliverables

Define every required file before filming. A “master video” is not a complete distribution plan.

| Channel | Audience / objective | Ratio | Duration | Language / captions | CTA |
| --- | --- | --- | --- | --- | --- |
| Website |  | 16:9 |  |  |  |
| Instagram / Facebook |  | 9:16 |  |  |  |
| TikTok |  | 9:16 |  |  |  |
| LinkedIn |  | 1:1 / 4:5 / 16:9 |  |  |  |
| YouTube |  | 16:9 / 9:16 |  |  |  |
| Other |  |  |  |  |  |

## File list

| Deliverable | Quantity / specs | Required |
| --- | --- | --- |
| Master film |  | [ ] |
| Vertical cutdowns |  | [ ] |
| Horizontal cutdowns |  | [ ] |
| Clean masters (no text) |  | [ ] |
| Captioned exports |  | [ ] |
| SRT files |  | [ ] |
| Thumbnails / cover frames |  | [ ] |
| Edited photos |  | [ ] |
| Raw footage / project archive |  | [ ] |

# 04  Creative direction and language

| Tone and personality | Premium, direct, warm, documentary, energetic... ________________________________________________________________ |
| --- | --- |

| Visual references | 2–4 links + what is useful in each ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| What must not be copied | ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| Brand rules | Logo, colours, typography, product display, claims ________________________________________________________________ |
| --- | --- |

| Language | Audience | Use | Separate master? |
| --- | --- | --- | --- |
| Darija |  | Performance / voice-over / captions |  |
| French |  | Performance / voix-off / sous-titres |  |
| Arabic |  | Performance / voix-off / sous-titres |  |
| English |  | Performance / voice-over / captions |  |

## Hook and CTA bank

| Item | Exact wording | Proof / destination |
| --- | --- | --- |
| Hook 1 |  |  |
| Hook 2 |  |  |
| Hook 3 |  |  |
| CTA 1 |  |  |
| CTA 2 |  |  |

# 05  Production reality

| Locations | Address, owner, access hours, parking, sound, power ________________________________________________________________ |
| --- | --- |

| People on camera | Names, roles, availability, consent ________________________________________________________________ |
| --- | --- |

| Products / props | Models, quantities, preparation, backup ________________________________________________________________ |
| --- | --- |

| Operating processes | What can actually happen on camera? ________________________________________________________________ |
| --- | --- |

| Travel / logistics | Cities, transfers, accommodation, load-in ________________________________________________________________ |
| --- | --- |

| Drone | Exact shot purpose, coordinates, import/permit status, fallback ________________________________________________________________ |
| --- | --- |

| Weather dependency | Thresholds, reserve day, indoor alternative ________________________________________________________________ |
| --- | --- |

| Sensitive information | Screens, records, patients, employees, confidential areas ________________________________________________________________ |
| --- | --- |

# 06  Rights, approvals and schedule

| Right | Scope required | Owner | Confirmed |
| --- | --- | --- | --- |
| Talent / employee image | Territory, term, media, paid use |  |  |
| Location | Filming, aerial, branding, hours, restoration |  |  |
| Music | Track / library, territory, term, paid media |  |  |
| Archive / third-party media | Source, owner, license |  |  |
| Product / trademarks | Approval and restrictions |  |  |

## Approval gates

| Gate | Approver | Response deadline |
| --- | --- | --- |
| Brief lock |  |  |
| Treatment / concept |  |  |
| Script / storyboard |  |  |
| Schedule / call sheet |  |  |
| Rough cut |  |  |
| Picture lock |  |  |
| Final masters |  |  |

| Maximum feedback rounds | ________ |
| --- | --- |

| Launch date and immovable dependencies | ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

# 07  Budget and success

| Available budget band | Dhs __________________ |
| --- | --- |

| Non-negotiable outcome | ________________________________________________________________ ________________________________________________________________ |
| --- | --- |

| Elements that may be reduced | Locations, versions, talent, duration, art direction, travel... ________________________________________________________________ |
| --- | --- |

| Optional upgrades | Drone, motion design, extra language, stills, reserve day... ________________________________________________________________ |
| --- | --- |

## Measurement plan

| Metric | Definition | Where measured |
| --- | --- | --- |
| Primary business KPI |  |  |
| Secondary KPI |  |  |
| Tracking owner |  |  |
| Measurement period |  |  |
| Baseline / target |  |  |

## Final production-ready checklist

[ ] One audience and one primary action

[ ] Single message and approved proof

[ ] Exact files by ratio, duration and language

[ ] Locations, people and products confirmed

[ ] Rights and consent route confirmed

[ ] Budget band and exclusions clear

[ ] One final approver and feedback dates

[ ] Fallbacks for weather, access and drone

Ready for production? The brief is ready when unknowns are visible, not when every line is filled. Share it with the production partner, confirm assumptions and lock the version used for quotation.